## Estimated Time
Task | Description | Time (H) | Remarks/Assumptions
WordPress installation and setup |  | 0.3
Events custom post type creation along with the 'tags' taxonomy | Create a custom post type for events where the imported data will be placed. | 0.5
Custom fields creation where the imported data will be saved |  | 0.5 | I will install the Advance Custom Fields plugin to create the custom fields i.e. organizer, email, latitute, longitude, etc.
Script to Import the JSON file | Import JSON file and save the data in the custom fields. In case of running the import multiple times, already imported events will be updated and new ones will be imported | 4 | I will create a JSON file from the data you have provided. I will place it in the directory and read it once the trigger is called via WP CLI.
Send an automated email once the import is finished | Send an email to logging@agentur-loop.com after the successful import with the details regarding the import | 1.5 | I will use WP mail SMTP plugin to configure mails on localhost.
Create a frontend page to display all the events | Display latest events first and display the times in relative time format | 1 | I will use bootstrap to achieve the front end page. However, this can be done without using Boostrap. I will use wp_enqueue hook to include the style and JS file for Bootstrap.
Script to export the events in JSON file |  | 2 | This can be achieved via wp JSON APIs, however, I will write a custom script for it.
Total time estimated |  | 9.8

## Tracked Time
Task | Description | Time (H) | Remarks/Assumptions
WordPress installation and setup |  | 0.3
Events custom post type creation along with the 'tags' taxonomy | Create a custom post type for events where the imported data will be placed. | 0.3
Custom fields creation where the imported data will be saved |  | 0.3 | I will install the Advance Custom Fields plugin to create the custom fields i.e. organizer, email, latitute, longitude, etc.
Script to Import the JSON file | Import JSON file and save the data in the custom fields. In case of running the import multiple times, already imported events will be updated and new ones will be imported | 3.5 | I will create a JSON file from the data you have provided. I will place it in the directory and read it once the trigger is called via WP CLI.
Send an automated email once the import is finished | Send an email to logging@agentur-loop.com after the successful import with the details regarding the import | 2.5 | I will use WP mail SMTP plugin to configure mails on localhost.
Create a frontend page to display all the events | Display latest events first and display the times in relative time format | 0.7 | I will use bootstrap to achieve the front end page. However, this can be done without using Boostrap. I will use wp_enqueue hook to include the style and JS file for Bootstrap.
Script to export the events in JSON file |  | 2.5 | This can be achieved via wp JSON APIs, however, I will write a custom script for it.
Total time estimated |  | 10.1